## Instructions
RISK TREATMENT PLAN & STATEMENT OF APPLICABILITY
Tumaini Capital Ltd ¦ ISO/IEC 27001:2022 — Clauses 6.1.3 & 6.1.3(d) ¦ ISMS-DOC-007 v1.0 ¦ Fictional case study
PURPOSE
This workbook contains two mandatory ISMS artefacts required by ISO/IEC 27001:2022 Clause 6.1.3: 1. Risk Treatment Plan (RTP) — documents the specific actions Tumaini Capital will take to treat each identified risk, organised into four implementation phases across the 12-month certification journey. 2. Statement of Applicability (SoA) — lists all 93 Annex A controls, states whether each is applicable or not, documents the implementation status, and records the justification for inclusion or exclusion.
WHY THE SoA IS THE MOST IMPORTANT ISMS DOCUMENT
The SoA is the primary reference document for the Stage 2 certification audit. The auditor uses it to plan every line of evidence-gathering. It must be consistent with the risk assessment (the risks drive the control selection) and with the risk treatment plan (the SoA records whether controls are implemented). Any control listed as 'Implemented' in the SoA must have auditable evidence to support that claim.
IMPLEMENTATION STATUS KEY
Implemented — The control is fully in place and evidence is available.
Partially Implemented — The control exists in some form but is informal, incomplete, or lacks documentation.
Planned — The control is identified as required but has not yet been implemented. A target date is assigned in the RTP.
N/A — The control is not applicable to the defined ISMS scope. A justification is documented.
JUSTIFICATION DRIVER KEY (SoA column 6)
RT = Risk Treatment: included because a risk assessment identified this control as necessary to treat a risk.
L = Legal/Regulatory: required by the Data Protection Act 2019, CBK guidance, or the Computer Misuse and Cybercrimes Act 2018.
C = Contractual: required by the bank partner due-diligence requirements or supplier agreements.
RT/L = Both risk treatment and legal requirement apply.
BP = Best Practice: included as a baseline control even where no specific risk or legal driver was identified.
IMPLEMENTATION PHASES
Phase 1 (Months 1–3): Foundation — Critical and High priority controls. Must be in place before Stage 1 audit.
Phase 2 (Months 3–6): Core Controls — Remaining High and key Medium priority controls.
Phase 3 (Months 6–9): Advanced Controls — Technical hardening, BCP, SDLC, and monitoring.
Phase 4 (Months 9–12): Audit Readiness — Internal audit, management review, Stage 1 and Stage 2 preparation.
ISMS-DOC-007 v1.0 ¦ Tumaini Capital Ltd ¦ RTP & SoA ¦ Fictional case study

## Risk Treatment Plan
RISK TREATMENT PLAN
Tumaini Capital Ltd ¦ ISO/IEC 27001:2022 — Clause 6.1.3 ¦ June 2026 ¦ Fictional case study
Action ID | Implementation Task | Related Risk(s) | Phase | Priority | Owner | Annex A / Clause Ref | Target Date | Success Measure
Phase 1 — Foundation (Months 1–3)
RTP-001 | Formally appoint ISMS Lead with documented authority and cross-departmental mandate. Communicate appointment to all staff. | R-007, R-012, R-021 | Phase 1 | HIGH | CEO | Cl.5.3, A.5.2 | Month 1 | Signed appointment letter; org-wide communication issued
RTP-002 | Draft, obtain CEO approval, and communicate overarching Information Security Policy. | R-001 – R-023 | Phase 1 | CRITICAL | ISMS Lead / CEO | A.5.1 | Month 1 | Signed policy published on company intranet; staff confirmation of receipt logged
RTP-003 | Implement Joiner/Mover/Leaver (JML) process: access provisioning approval workflow, mandatory 24-hr deactivation SLA on exit. | R-001 | Phase 1 | CRITICAL | Head of Engineering / HR | A.5.16, A.5.18, A.6.5 | Month 1 | JML procedure document approved; first leaver processed through new workflow within 24 hrs
RTP-004 | Conduct immediate access review across all in-scope systems (AWS, CRM, Google Workspace). Remove or adjust any inappropriate access rights. | R-001, R-012 | Phase 1 | CRITICAL | Head of Engineering | A.5.15, A.5.18, A.8.2 | Month 1 | Access review log signed off; all orphaned or excessive accounts remediated
RTP-005 | Mandate and implement MFA for all AWS, CRM, and Google Workspace access. Define MFA-exempt exceptions with compensating controls. | R-002, R-016 | Phase 1 | HIGH | Head of Engineering | A.5.17, A.8.5 | Month 2 | MFA enforced for 100% of admin and remote access accounts; exceptions documented
RTP-006 | Design and deliver initial mandatory security awareness training for all 85 staff covering: phishing, data handling, AUP, and incident reporting. | R-002, R-010 | Phase 1 | HIGH | ISMS Lead | A.6.3 | Month 2 | Training completion rate ≥90%; attendance record maintained
RTP-007 | Draft, approve, and communicate Incident Response Policy and Procedure. Define roles (Incident Manager, technical responders, comms lead). | R-007 | Phase 1 | CRITICAL | ISMS Lead | A.5.24, A.5.25, A.5.26 | Month 2 | IR procedure approved; roles assigned; tabletop exercise scheduled
RTP-008 | Verify backup configuration for all in-scope systems. Define RTO/RPO targets. Test and document recovery procedure. | R-008 | Phase 1 | HIGH | Head of Engineering | A.8.13, A.8.14, A.5.30 | Month 2 | Backup policy approved; recovery test completed and results documented
RTP-009 | Draft and approve Acceptable Use Policy (AUP) including BYOD requirements, remote working standards, and social media use. | R-002, R-005, R-010 | Phase 1 | HIGH | ISMS Lead | A.5.10, A.6.7 | Month 2 | AUP signed by all staff; BYOD addendum acknowledged by BYOD users
RTP-010 | Define and enforce organisation-wide password policy (minimum 12 chars, complexity, no reuse). Apply via directory services where possible. | R-016 | Phase 1 | HIGH | Head of Engineering | A.5.17 | Month 3 | Password policy published; technical enforcement confirmed across all systems
Phase 2 — Core Controls (Months 3–6)
RTP-011 | Implement vulnerability scanning programme: AWS Inspector for cloud, endpoint scanner for laptops. Define patching SLAs (critical: 72 hrs, high: 14 days). | R-009 | Phase 2 | HIGH | Head of Engineering | A.8.8 | Month 4 | First scan completed; vulnerability register created; patching SLA documented and tracked
RTP-012 | Define cloud security policy covering AWS shared responsibility, configuration baselines (CIS AWS Benchmark), and change control. | R-003 | Phase 2 | HIGH | Head of Engineering | A.5.23, A.8.9 | Month 4 | Cloud security policy approved; AWS Config enabled; baseline deviations reviewed
RTP-013 | Audit all API credentials (M-Pesa, credit bureaus). Store secrets in AWS Secrets Manager. Implement rotation schedule. Enable API call monitoring. | R-006 | Phase 2 | HIGH | Head of Engineering | A.5.17, A.8.15, A.8.16 | Month 4 | All API keys in Secrets Manager; rotation schedule defined; CloudTrail monitoring alert configured
RTP-014 | Review and update MSP, M-Pesa, and credit bureau contracts to include information security requirements, NDA, and incident notification obligations. | R-013 | Phase 2 | HIGH | ISMS Lead / Legal | A.5.19, A.5.20 | Month 4 | Supplier contracts updated; supplier risk register created; annual review scheduled
RTP-015 | Define and implement logging policy. Enable AWS CloudTrail, CRM audit logs, and authentication logs. Set 12-month retention. | R-022 | Phase 2 | HIGH | Head of Engineering | A.8.15, A.8.16 | Month 5 | Logging policy approved; all required log sources enabled; 12-month retention confirmed
RTP-016 | Draft and approve Information Classification Policy with four-tier scheme (Public / Internal / Confidential / Restricted). Apply to all data stores. | R-001, R-003 | Phase 2 | HIGH | ISMS Lead | A.5.12, A.5.13 | Month 5 | Classification policy approved; data stores labelled; staff briefed on handling requirements
RTP-017 | Implement ROPA and privacy notices in compliance with the Data Protection Act, 2019. Conduct DPIA for the lending platform. | R-004, R-018 | Phase 2 | HIGH | ISMS Lead | A.5.34 | Month 5 | ROPA documented; privacy notices published; DPIA completed and signed off
RTP-018 | Complete and approve the formal Information Asset Register (building on this engagement's draft). Assign asset owners and classification. | R-001, R-003 | Phase 2 | MEDIUM | Head of Engineering | A.5.9 | Month 5 | Asset register approved; owners assigned; integrated into risk assessment process
RTP-019 | Implement privileged access management: inventory all admin accounts, enforce least privilege, separate admin from standard, quarterly PAM review. | R-012 | Phase 2 | HIGH | Head of Engineering | A.8.2, A.5.2, A.5.3 | Month 5 | PAM register created; all privileged accounts inventoried; least privilege applied; MFA on all admin accounts
RTP-020 | Draft and implement Data Subject Rights (DSR) handling procedure. Train responsible staff. Test end-to-end within the 21-day statutory window. | R-018 | Phase 2 | HIGH | ISMS Lead | A.5.34, A.5.33 | Month 6 | DSR procedure approved; responsible owner trained; test DSR completed within 21 days
Phase 3 — Advanced Controls (Months 6–9)
RTP-021 | Implement VLAN network segmentation separating user, management, server, and guest traffic at both Nairobi HQ and Kisumu office. | R-011 | Phase 3 | HIGH | Head of Engineering | A.8.22, A.8.20 | Month 7 | VLAN architecture documented; segmentation implemented and tested; penetration test confirms isolation
RTP-022 | Develop, document, and test Business Continuity Plan for the core lending platform. Define and test RTO/RPO. Confirm AWS multi-AZ configuration. | R-015 | Phase 3 | MEDIUM | Head of Engineering / ISMS Lead | A.5.29, A.5.30, A.8.14 | Month 7 | BCP approved; failover test completed; RTO/RPO confirmed and documented
RTP-023 | Define and implement Secure SDLC: security requirements gate, SAST/DAST in CI/CD pipeline, secure coding standards, annual developer training. | R-009 | Phase 3 | HIGH | Head of Engineering | A.8.25, A.8.26, A.8.28, A.8.29 | Month 7 | Secure SDLC policy approved; SAST tool integrated in pipeline; first scan completed
RTP-024 | Implement data masking for all non-production environments. Enforce strict dev/test/prod separation. Prohibit real customer data in test. | R-014 | Phase 3 | HIGH | Head of Engineering | A.8.11, A.8.31, A.8.33 | Month 8 | Data masking implemented; environment separation confirmed; no production data in test verified
RTP-025 | Verify and enforce full-disk encryption (BitLocker/FileVault) on all company laptops. Implement remote wipe capability for corporate data on BYOD. | R-017 | Phase 3 | MEDIUM | Head of Engineering | A.7.9, A.8.1 | Month 8 | 100% of company laptops confirmed encrypted; remote wipe tested on BYOD sample
RTP-026 | Deploy DNS-based web filtering (Cloudflare Gateway or equivalent). Confirm AV deployment and configuration on all managed endpoints. | R-005 | Phase 3 | MEDIUM | Head of Engineering | A.8.7, A.8.23 | Month 8 | Web filtering deployed; AV coverage 100% of managed endpoints confirmed
RTP-027 | Deploy security monitoring: AWS CloudWatch anomaly detection + CloudTrail alerting. Define alert thresholds and escalation procedure. | R-022 | Phase 3 | HIGH | Head of Engineering | A.8.16 | Month 8 | Monitoring alerts configured; escalation procedure defined; first alert test completed
RTP-028 | Conduct physical security assessment at Nairobi HQ and Kisumu office. Implement visitor register. Assess CCTV feasibility for server/network areas. | R-023 | Phase 3 | MEDIUM | Head of Operations | A.7.1, A.7.2, A.7.4 | Month 8 | Assessment completed; visitor register in place; CCTV decision documented
RTP-029 | Conduct tabletop incident response exercise testing the IR procedure across ISMS Lead, Engineering, and Operations. | R-007 | Phase 3 | HIGH | ISMS Lead | A.5.26 | Month 9 | Tabletop exercise completed; lessons learned documented; IR procedure updated
RTP-030 | Draft and approve Information Transfer Policy defining approved channels, prohibited sharing methods, and encryption requirements. | R-020 | Phase 3 | MEDIUM | ISMS Lead | A.5.14 | Month 9 | Information Transfer Policy approved; staff briefed; WhatsApp Business acceptable use guidance published
Phase 4 — Audit Readiness (Months 9–12)
RTP-031 | Conduct first internal ISMS audit covering all in-scope clauses and Annex A controls. Document findings and corrective actions. | All | Phase 4 | HIGH | ISMS Lead | Cl.9.2 | Month 10 | Internal audit report issued; all major nonconformities have corrective action plans
RTP-032 | Conduct first formal ISMS management review. Present risk register, audit results, objective progress, and resource requirements. | All | Phase 4 | HIGH | CEO / ISMS Lead | Cl.9.3 | Month 10 | Management review minutes approved and signed by CEO; action items assigned
RTP-033 | Finalise and obtain approval for the Statement of Applicability. Ensure all Planned controls have evidence of progress or scheduled completion. | All | Phase 4 | CRITICAL | ISMS Lead | Cl.6.1.3 | Month 10 | SoA v1.0 signed off by ISMS Lead and CEO; made available for Stage 1 auditor
RTP-034 | Compile Stage 1 audit documentation pack: scope statement, SoA, risk register, RTP, context doc, policies, and management review minutes. | All | Phase 4 | CRITICAL | ISMS Lead | Cl.7.5 | Month 11 | Audit pack complete; no unresolved Clause 4–10 documentation gaps; Stage 1 audit scheduled
RTP-035 | Address all Stage 1 audit findings. Confirm readiness for Stage 2. Brief key staff on audit process and their evidence obligations. | All | Phase 4 | CRITICAL | ISMS Lead / CEO | All | Month 12 | All Stage 1 observations addressed; Stage 2 audit scheduled and conducted

## Statement of Applicability
STATEMENT OF APPLICABILITY (SoA)
Tumaini Capital Ltd ¦ ISO/IEC 27001:2022 — Annex A ¦ All 93 Controls ¦ ISMS-DOC-007 v1.0 ¦ Fictional case study
Driver key: RT = Risk Treatment ¦ L = Legal/Regulatory (DPA 2019 / CBK / Computer Misuse Act) ¦ C = Contractual (bank partner) ¦ BP = Best Practice
Control Ref | Control Name | Applicable? | Justification for Inclusion / Exclusion | Implementation Status | Driver | Risk Reference(s) | RTP Action(s) | Evidence / Document Reference
── THEME 1: ORGANIZATIONAL CONTROLS (A.5) — 37 Controls
A.5.1 | Policies for information security | Yes | Foundation control required across all Annex A themes; absence is the root cause of most other gaps. | Planned | RT/L/C | R-001–R-023 | RTP-002 | To be developed: Information Security Policy suite (ISMS-DOC-010)
A.5.2 | Information security roles and responsibilities | Yes | No formal accountability for information security exists; ISMS Lead appointment is a prerequisite for certification. | Planned | RT | R-007, R-012, R-021 | RTP-001 | To be developed: Roles & Responsibilities document
A.5.3 | Segregation of duties | Yes | Flat Engineering team holds admin and change approval rights without oversight; segregation required to reduce insider risk. | Partially Implemented | RT | R-012 | RTP-019 | AWS IAM policy partially separates roles — formal documentation pending
A.5.4 | Management responsibilities | Yes | Required to embed security obligations into staff management; supports disciplinary and awareness controls. | Planned | RT | R-010, R-021 | RTP-002 | To be included in IS Policy and updated job descriptions
A.5.5 | Contact with authorities | Yes | Required for ODPC breach notification (72-hr window) and CBK incident reporting obligations. | Planned | L | R-004, R-007 | RTP-007 | To be included in Incident Response Procedure
A.5.6 | Contact with special interest groups | Yes | Supports threat intelligence gathering relevant to Kenyan fintech sector; KE-CIRT membership recommended. | Planned | BP | — | — | No current contact — KE-CIRT subscription to be established
A.5.7 | Threat intelligence | Yes | Active threat landscape targeting mobile-money fintech requires structured intelligence gathering. | Planned | RT | R-002, R-005 | — | No process — to be established via threat feed subscriptions
A.5.8 | Information security in project management | Yes | New features deployed on lending platform without security review; control needed to prevent introducing vulnerabilities. | Planned | RT | R-009 | RTP-023 | To be embedded in SDLC policy
A.5.9 | Inventory of information and other associated assets | Yes | Asset register is prerequisite for risk assessment and access control; draft produced in this engagement. | Partially Implemented | RT | R-001, R-003 | RTP-018 | Draft: Asset Register (ISMS-DOC-006 Tab 2) — formal approval pending
A.5.10 | Acceptable use of information and other associated assets | Yes | No AUP exists; staff use BYOD and WhatsApp Business for business without documented acceptable use standards. | Planned | RT | R-002, R-010, R-020 | RTP-009 | To be developed: Acceptable Use Policy
A.5.11 | Return of assets | Yes | CRM incident directly caused by failure to recover access credentials on staff exit. | Planned | RT | R-001 | RTP-003 | To be included in offboarding procedure
A.5.12 | Classification of information | Yes | KYC and financial data require higher protection levels than general working documents; classification scheme is foundational. | Planned | RT/L | R-001, R-003 | RTP-016 | To be developed: Information Classification Policy
A.5.13 | Labelling of information | Yes | Required once classification scheme is established to ensure consistent handling. | Planned | RT | R-001, R-003 | RTP-016 | Dependent on classification policy — to be implemented concurrently
A.5.14 | Information transfer | Yes | KYC documents and financial data transferred via email and WhatsApp without defined security requirements. | Planned | RT/L | R-020 | RTP-030 | To be developed: Information Transfer Policy
A.5.15 | Access control | Yes | Absence of access control policy was the root cause of the CRM unauthorized-access incident. | Planned | RT | R-001, R-012 | RTP-003, RTP-004 | To be developed: Access Control Policy
A.5.16 | Identity management | Yes | No identity lifecycle management; user accounts created and deleted on an ad-hoc basis with no oversight. | Planned | RT | R-001, R-012 | RTP-003 | To be included in JML process documentation
A.5.17 | Authentication information | Yes | No consistent password standards; MFA not mandated; credential compromise is a top-ranked threat vector. | Partially Implemented | RT | R-002, R-006, R-016 | RTP-005, RTP-010 | Password controls partially exist at system level — policy and MFA enforcement pending
A.5.18 | Access rights | Yes | No formal process for granting, reviewing, or revoking access rights across any in-scope system. | Planned | RT | R-001, R-012 | RTP-003, RTP-004 | To be included in Access Control Policy and JML process
A.5.19 | Information security in supplier relationships | Yes | MSP, M-Pesa API, and credit bureaus all access in-scope data without documented security requirements. | Planned | RT/C | R-013 | RTP-014 | To be developed: Supplier Risk Management Policy
A.5.20 | Addressing information security within supplier agreements | Yes | Existing contracts with MSP, M-Pesa, and credit bureaus contain no information security clauses. | Planned | RT/C | R-013 | RTP-014 | Existing contracts to be updated; new standard security schedule to be drafted
A.5.21 | Managing information security in the ICT supply chain | Yes | Lending platform depends on AWS and third-party APIs whose security posture must be understood and managed. | Planned | RT | R-003, R-006, R-013 | RTP-014 | To be included in Supplier Risk Management Policy
A.5.22 | Monitoring, review and change management of supplier services | Yes | No supplier performance review process; security incidents at suppliers may go undetected. | Planned | RT | R-013 | RTP-014 | Annual supplier review cycle to be established
A.5.23 | Information security for use of cloud services | Yes | Core lending platform hosted on AWS; shared responsibility model not formally documented or policy-governed. | Partially Implemented | RT | R-003 | RTP-012 | AWS deployed and operational — cloud security policy and CIS baselines pending
A.5.24 | Information security incident management planning and preparation | Yes | Organisation has experienced a security incident with no formal response process. Mandatory for certification. | Planned | RT | R-007 | RTP-007 | To be developed: Incident Response Policy and Procedure
A.5.25 | Assessment and decision on information security events | Yes | No capability to distinguish security events from normal activity without a classification framework. | Planned | RT | R-007, R-022 | RTP-007 | To be included in Incident Response Procedure
A.5.26 | Response to information security incidents | Yes | Ad-hoc response to prior CRM incident demonstrated this gap with documented consequences. | Planned | RT | R-007 | RTP-007, RTP-029 | To be developed: Incident Response Procedure + tabletop exercise
A.5.27 | Learning from information security incidents | Yes | Root cause analysis and lessons learned were not conducted after the CRM access incident. | Planned | RT | R-007 | RTP-007 | Post-incident review process to be included in IR Procedure
A.5.28 | Collection of evidence | Yes | Forensic evidence collection required to support potential ODPC or law enforcement reporting after incidents. | Planned | RT/L | R-007 | RTP-007 | To be included in Incident Response Procedure
A.5.29 | Information security during disruption | Yes | No continuity arrangements for information security controls during a disruptive event. | Planned | RT | R-015 | RTP-022 | To be developed: Business Continuity Plan
A.5.30 | ICT readiness for business continuity | Yes | AWS provides infrastructure redundancy but RTO/RPO for the lending platform are undefined and untested. | Partially Implemented | RT | R-015 | RTP-008, RTP-022 | AWS multi-AZ configured — formal BCP and recovery test pending
A.5.31 | Legal, statutory, regulatory and contractual requirements | Yes | DPA 2019, CBK digital credit guidance, Computer Misuse and Cybercrimes Act 2018 all impose information security obligations. | Partially Implemented | L | R-004, R-018 | — | Informal compliance tracking — formal compliance register to be developed
A.5.32 | Intellectual property rights | Yes | Lending platform source code is a key IP asset; software licensing compliance required. | Planned | BP | — | — | Software licence register and IP policy to be developed
A.5.33 | Protection of records | Yes | ISMS records and customer data must be retained per defined schedules in compliance with the DPA 2019. | Planned | RT/L | R-001, R-018 | RTP-020 | Records retention policy to be developed; data map to be completed
A.5.34 | Privacy and protection of PII | Yes | 120,000 borrowers' personal and financial data processed; ODPC compliance is a primary certification driver. | Partially Implemented | RT/L | R-004, R-018 | RTP-017, RTP-020 | Informal ODPC awareness — ROPA, privacy notices, DPIA, and DSR procedure pending
A.5.35 | Independent review of information security | Yes | Mandatory internal audit required before Stage 2 certification audit. | Planned | RT | All | RTP-031 | First internal audit scheduled: Month 10
A.5.36 | Compliance with policies, rules and standards for information security | Yes | Policies must be verifiably followed once established; compliance monitoring needed for certification evidence. | Planned | RT | All | — | Compliance monitoring programme to be established post-policy implementation
A.5.37 | Documented operating procedures | Yes | Critical operational procedures (backups, access provisioning, patching, incident response) are undocumented. | Partially Implemented | RT | R-007, R-008, R-009 | RTP-007, RTP-008 | Some informal Engineering runbooks — formal approval and document control pending
── THEME 2: PEOPLE CONTROLS (A.6) — 8 Controls
A.6.1 | Screening | Yes | Roles with access to customer financial data and AWS infrastructure require consistent background checking. | Partially Implemented | RT | — | — | Informal screening for Engineering roles — policy and consistent application pending
A.6.2 | Terms and conditions of employment | Yes | Employment contracts must reference information security responsibilities and the IS Policy. | Partially Implemented | RT | — | — | Contracts exist — IS Policy reference to be added at next contract review
A.6.3 | Information security awareness, education and training | Yes | Untrained staff are the primary human-factor risk vector; awareness training is mandatory for all 85 staff. | Planned | RT | R-002, R-010 | RTP-006 | First awareness training session: Month 2. Annual programme to be established.
A.6.4 | Disciplinary process | Yes | Disciplinary framework must explicitly address information security violations to act as a deterrent. | Partially Implemented | RT | — | — | General disciplinary process exists — IS violation clause to be added
A.6.5 | Responsibilities after termination or change of employment | Yes | CRM access incident was a direct result of a failure in post-termination access revocation. | Planned | RT | R-001 | RTP-003 | To be documented in offboarding procedure as part of JML process
A.6.6 | Confidentiality or non-disclosure agreements | Yes | All staff and contractors with access to in-scope customer or financial data must sign NDAs. | Partially Implemented | RT/C | — | RTP-014 | NDAs in place for senior staff — consistent application and supplier NDA pending
A.6.7 | Remote working | Yes | Staff work remotely and use BYOD without documented security requirements for the remote environment. | Planned | RT | R-002, R-017 | RTP-009 | To be included in AUP / Remote Working Policy
A.6.8 | Information security event reporting | Yes | No reporting channel exists; staff would not know how or what to report without documented guidance. | Planned | RT | R-010 | RTP-007 | To be included in Incident Response Procedure and awareness training
── THEME 3: PHYSICAL CONTROLS (A.7) — 14 Controls
A.7.1 | Physical security perimeters | Yes | Both offices house staff with access to in-scope systems; physical perimeters must be defined and controlled. | Partially Implemented | RT | R-023 | RTP-028 | Building perimeters and reception access informally controlled — formal policy and assessment pending
A.7.2 | Physical entry | Yes | Unauthorised entry at either office could enable device theft or network access. | Partially Implemented | RT | R-023 | RTP-028 | Security guards in place — electronic access logs absent; visitor register to be implemented
A.7.3 | Securing offices, rooms and facilities | Yes | Offices contain devices and network access points that require physical protection. | Partially Implemented | RT | R-023 | RTP-028 | Offices locked outside hours — clean desk and secure area assessment pending
A.7.4 | Physical security monitoring | Yes | CCTV or equivalent monitoring needed at server/network areas especially at Kisumu office. | Planned | RT | R-023 | RTP-028 | No CCTV — feasibility assessment to be conducted in Phase 3
A.7.5 | Protecting against physical and environmental threats | Yes | Both offices require assessment for fire, flood, power, and physical threat mitigation. | Partially Implemented | RT | — | RTP-028 | AWS physical controls covered by AWS attestation; offices not formally assessed
A.7.6 | Working in secure areas | Yes | Any area containing network equipment or server access requires defined working controls. | Planned | RT | — | RTP-028 | To be addressed as part of physical security assessment
A.7.7 | Clear desk and clear screen | Yes | Physical documents containing customer data and unattended screens with system access are a data exposure risk. | Planned | RT | — | RTP-009 | Clear desk and screen lock policy to be included in AUP
A.7.8 | Equipment siting and protection | Yes | Laptops and network equipment at both offices require protection from physical damage and eavesdropping. | Partially Implemented | BP | — | — | Informal practices — equipment protection guidelines to be included in AUP
A.7.9 | Security of assets off-premises | Yes | Staff carry company laptops off-premises and use BYOD phones without documented off-premises security requirements. | Planned | RT | R-017 | RTP-009, RTP-025 | To be included in AUP and Remote Working Policy
A.7.10 | Storage media | Yes | USB drives used informally; potential data exfiltration vector from a fintech handling sensitive KYC data. | Planned | RT | R-005 | — | Media management policy to be developed; USB restriction to be assessed
A.7.11 | Supporting utilities | Yes | Power continuity for Kisumu office and confirmation of UPS for Nairobi HQ are required for availability. | Partially Implemented | RT | R-015 | RTP-022 | AWS provides cloud utility resilience — office supporting utilities to be formally assessed
A.7.12 | Cabling security | Yes | Network cabling at both offices requires protection from interference and damage. | Partially Implemented | BP | — | — | Cabling exists — formal assessment and labelling to be completed
A.7.13 | Equipment maintenance | Yes | MSP maintains laptops — a documented maintenance schedule and security requirements are needed. | Partially Implemented | RT | R-013 | RTP-014 | Informal MSP maintenance — schedule and minimum security standard to be included in MSP contract
A.7.14 | Secure disposal or re-use of equipment | Yes | Devices must be securely wiped before disposal or reuse to prevent customer data exposure. | Planned | RT/L | R-017 | — | No disposal procedure — to be developed; data erasure certification required
── THEME 4: TECHNOLOGICAL CONTROLS (A.8) — 34 Controls
A.8.1 | User endpoint devices | Yes | ~85 company laptops and BYOD phones used to access in-scope systems without a documented endpoint security standard. | Partially Implemented | RT | R-005, R-017 | RTP-025, RTP-026 | Devices exist and are MSP-managed — endpoint security policy, encryption, and AV confirmation pending
A.8.2 | Privileged access rights | Yes | Admin accounts in AWS and CRM are not inventoried, reviewed, or managed to least-privilege principles. | Planned | RT | R-012 | RTP-019 | No PAM — privileged account inventory and least-privilege enforcement to be implemented
A.8.3 | Information access restriction | Yes | Access restrictions exist at system level but are not backed by a policy or subject to periodic review. | Partially Implemented | RT | R-001, R-012 | RTP-003, RTP-004 | Technical controls in place — Access Control Policy and access review process pending
A.8.4 | Access to source code | Yes | Lending platform source code is a critical IP asset; access must be restricted to authorised developers only. | Partially Implemented | RT | R-019 | — | Code repository exists — formal access controls and audit logging to be implemented
A.8.5 | Secure authentication | Yes | No MFA mandated; authentication standards vary by system; credential attacks are a high-ranked threat. | Partially Implemented | RT | R-002, R-016 | RTP-005 | Some systems have authentication — MFA and organisation-wide password policy pending
A.8.6 | Capacity management | Yes | AWS auto-scaling provides partial capacity management; no formal capacity plan or defined thresholds. | Partially Implemented | RT | R-015 | — | AWS auto-scaling configured — capacity management procedure and CloudWatch thresholds pending
A.8.7 | Protection against malware | Yes | Ransomware and malware via phishing are realistic threats; AV deployment status is unconfirmed. | Partially Implemented | RT | R-005 | RTP-026 | MSP may have deployed AV — coverage and configuration to be confirmed and documented
A.8.8 | Management of technical vulnerabilities | Yes | No vulnerability scanning or patch management; unpatched systems are a primary attack surface. | Planned | RT | R-009 | RTP-011 | No programme — AWS Inspector and endpoint scanner to be deployed
A.8.9 | Configuration management | Yes | AWS infrastructure is configured without formal baselines; configuration drift could introduce vulnerabilities. | Partially Implemented | RT | R-003 | RTP-012 | AWS configured — CIS Benchmark baselines and AWS Config for drift detection pending
A.8.10 | Information deletion | Yes | Customer data must be deleted in accordance with retention schedules under the DPA 2019. | Planned | RT/L | R-001, R-004 | RTP-020 | No automated deletion process — Records Management Policy and data deletion procedure pending
A.8.11 | Data masking | Yes | Production KYC and financial data may be used in test environments creating a data protection risk. | Planned | RT/L | R-014 | RTP-024 | No masking implemented — to be deployed in all non-production environments
A.8.12 | Data leakage prevention | Yes | Sensitive data patterns (KYC, financial) could be exfiltrated via email or cloud storage without DLP controls. | Planned | RT | R-001, R-005 | — | No DLP — email DLP rules for sensitive data patterns to be assessed and implemented
A.8.13 | Information backup | Yes | Core lending platform data is revenue-critical; backup failure with no tested recovery is a Critical risk. | Partially Implemented | RT | R-008 | RTP-008 | AWS storage redundancy exists — backup policy, defined RTO/RPO, and tested recovery pending
A.8.14 | Redundancy of information processing facilities | Yes | Lending platform availability is critical; AWS multi-AZ capability must be formally configured and tested. | Partially Implemented | RT | R-015 | RTP-022 | AWS multi-AZ capability available — formal configuration, testing, and documentation pending
A.8.15 | Logging | Yes | Logging is the primary means of detecting and investigating security incidents; policy and consistent coverage needed. | Partially Implemented | RT | R-006, R-022 | RTP-013, RTP-015 | CloudTrail and some app logs exist — Logging Policy, complete coverage, and 12-month retention pending
A.8.16 | Monitoring activities | Yes | Security events go undetected without a monitoring programme; a fintech holding financial data is a high-value target. | Planned | RT | R-022 | RTP-015, RTP-027 | No monitoring programme — CloudWatch anomaly detection and alert thresholds to be configured
A.8.17 | Clock synchronisation | Yes | Accurate timestamps are required for forensic investigation and log correlation across systems. | Partially Implemented | BP | — | — | AWS infrastructure uses NTP by default — endpoint synchronisation to be verified and documented
A.8.18 | Use of privileged utility programs | Yes | Admin tools accessible to the Engineering team without access controls or usage logging. | Partially Implemented | RT | R-012 | RTP-019 | Admin tools in use — access restrictions and audit logging to be implemented
A.8.19 | Installation of software on operational systems | Yes | Unapproved software could introduce malware or security vulnerabilities on company endpoints. | Planned | RT | R-005 | — | No approved software list — endpoint management policy and software restriction to be implemented
A.8.20 | Networks security | Yes | Office networks managed by MSP without a documented network security policy or architecture review. | Partially Implemented | RT | R-011 | RTP-021 | Network exists and is operational — network security policy and architecture documentation pending
A.8.21 | Security of network services | Yes | M-Pesa API and credit bureau connections require defined security requirements for data in transit. | Partially Implemented | RT | R-006 | RTP-013 | TLS in transit for M-Pesa — formal network services security requirements to be documented
A.8.22 | Segregation of networks | Yes | Flat office network enables lateral movement from a compromised endpoint to core systems. | Planned | RT | R-011 | RTP-021 | No segmentation — VLAN implementation planned for Phase 3
A.8.23 | Web filtering | Yes | Staff can access malicious web content without restriction; phishing and drive-by download risk. | Planned | RT | R-005 | RTP-026 | No web filtering — DNS-based filtering to be deployed in Phase 3
A.8.24 | Use of cryptography | Yes | KYC and financial data at rest and in transit require encryption; key management must be formalised. | Partially Implemented | RT/L | R-001, R-006 | RTP-012 | AWS encryption at rest (AES-256) and TLS in transit in place — Cryptography Policy and KMS key management pending
A.8.25 | Secure development life cycle | Yes | Lending platform is actively developed; security must be integrated into the SDLC to prevent introducing vulnerabilities. | Planned | RT | R-009 | RTP-023 | No secure SDLC — policy, SAST/DAST tooling, and developer training to be implemented
A.8.26 | Application security requirements | Yes | Security requirements are not defined at design stage; vulnerabilities may be built into new features. | Planned | RT | R-009 | RTP-023 | No application security requirements process — to be integrated into SDLC
A.8.27 | Secure system architecture and engineering principles | Yes | Security architecture principles (defence in depth, least privilege, secure defaults) are not applied consistently. | Planned | RT | R-003, R-011 | RTP-023 | No formal principles documented — to be defined and applied to all new system design
A.8.28 | Secure coding | Yes | No secure coding standards; OWASP Top 10 risks may be present in the lending platform codebase. | Planned | RT | R-009 | RTP-023 | No standards — Secure Coding Standard (OWASP-based) to be developed and training delivered
A.8.29 | Security testing in development and acceptance | Yes | No security testing in the CI/CD pipeline; vulnerabilities can reach production without detection. | Planned | RT | R-009 | RTP-023 | No testing — SAST and DAST to be integrated in pipeline; annual penetration test to be commissioned
A.8.30 | Outsourced development | No | Tumaini Capital conducts all software development in-house. There is no outsourced development activity within the defined ISMS scope. | N/A | — | — | — | Exclusion documented in SoA. To be reviewed if outsourced development commences.
A.8.31 | Separation of development, test and production environments | Yes | Dev/test environments may share production data or infrastructure, creating data exposure and change management risk. | Partially Implemented | RT | R-014 | RTP-024 | Some environment separation exists — formal policy, data masking, and strict separation controls pending
A.8.32 | Change management | Yes | Changes to the lending platform are made informally; unapproved changes could introduce vulnerabilities. | Partially Implemented | RT | R-003, R-009 | — | Informal Engineering change process — formal change management procedure to be documented
A.8.33 | Test information | Yes | Real customer KYC and financial data used in test environments is a data protection violation under the DPA 2019. | Planned | RT/L | R-014 | RTP-024 | No test data policy — data masking and synthetic data usage to be implemented
A.8.34 | Protection of information systems during audit testing | Yes | Audit and penetration testing tools could disrupt production systems without a defined rules-of-engagement process. | Planned | RT | — | RTP-031 | Rules of engagement for internal audit and penetration testing to be documented

## Implementation Roadmap
12-MONTH IMPLEMENTATION ROADMAP
Tumaini Capital Ltd ¦ ISO/IEC 27001:2022 ¦ Target: Month 12 Certification ¦ Fictional case study
Activity / Milestone | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
── PHASE 1: FOUNDATION (Months 1–3)
Appoint ISMS Lead formally | bar: M1
Information Security Policy approved
JML process implemented | bar: M1 to M2
Immediate access review completed
MFA mandated on all key systems | bar: M2 to M3
Security awareness training (initial)
Incident Response Procedure drafted | bar: M2 to M3
Backup procedures verified & tested
AUP / BYOD Policy approved | bar: M2 to M3
Organisation-wide password policy
── PHASE 2: CORE CONTROLS (Months 3–6)
Vulnerability scanning deployed
Cloud security policy & AWS baselines | bar: M4
API credential audit & Secrets Manager
Supplier contracts updated | bar: M4 to M5
Logging policy & CloudTrail enabled
Information Classification Policy | bar: M5
ROPA & privacy notices (DPA compliance)
Information Asset Register finalised | bar: M5
Privileged Access Management (PAM)
DSR procedure & DPIA completed | bar: M6
── PHASE 3: ADVANCED CONTROLS (Months 6–9)
VLAN network segmentation | bar: M7
Business Continuity Plan & failover test
Secure SDLC policy & SAST/DAST | bar: M7 to M8
Data masking & environment separation
Endpoint encryption & remote wipe | bar: M8
Web filtering & AV confirmation
Security monitoring (CloudWatch/SIEM) | bar: M8
Physical security assessment
IR tabletop exercise | bar: M9
Information Transfer Policy
── PHASE 4: AUDIT READINESS (Months 9–12)
Internal ISMS audit
First management review | bar: M10
SoA v1.0 finalised & approved
Stage 1 audit documentation pack | bar: M11
Stage 1 certification audit
Address Stage 1 findings | bar: M11 to M12
Stage 2 certification audit
Legend: | M1: Phase 1; M2: Phase 2; M3: Phase 3; M4: Phase 4